## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | TitleSearch | [6 empty] | Completed | 1
| Team Members: | Mina, Justin, Brandon, Jay, AJ | [6 empty] | Discarded | 2
| Date: | 2019-04-08 | Cycle: | 3 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | People seeking to purchase real estate must perform a “title search” to verify that none of the previous owners of the property over the past 40+ years still have any outstanding loans or liens on the residence. This process is expensive in terms of time and money. The aim of our software is to use artificial intelligence to automate this search, allowing people to bypass lawyers in lieu of quickly finding out property information for themselves. | [6 empty] | In Review
Unstarted
| Cycle Intent: | The intent of Cycle 3 is to create a robust, end-to-end design for searching for warranty deeds by book number and page number as well as first name and last name.
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Receive PDF of entered WD book and page number |  | 1 | 40 | 20 | Completed | 42 | 66
2 | Convert PDF into text document |  | 1 | 2 | 0 | Completed | 2 | 2
3 | Enter WD book and page number to get report on house |  | 1 | 3 | 3 | Collaboration | 5 | 5
4 | NLU - Analyze Text |  | 1 | 10 | 8 | Completed | 8 | 8
5 | NLU - Extract Grantor and Grantee from Waranty Deed |  | 2 | 10 | 2 | Completed | 3 | 3
6 | Search any term in document processed by Discovery |  | 1 | 15 | 0 | Completed | 20 | 20
7 | Store deeds in a functional database |  | 1 | 10 | 10 | Completed | 2 | 2
8 | Have Watson analyze types and subtypes relationships- Annotations |  | 1 | 10 | 3 | Completed | 3 | 3
9 | Watson learn how to automatically recognize Grantors and Grantees |  | 1 | 20 | 23 | In Review | 23 | 26
10 | Watson to be able to understand domain specific knowledge (Relationships) |  | 2 | 3 | 0 | Discarded | 0 | 0
11 | Generate report of the history of a house using warranty deeds. |  | 3 | 200 | 200 | Collaboration | 0 | 0
12 | Validation of NLU entity extraction by means of UI input boxes |  | 2 | 140 | 0 | Completed | 0 | 10
13 | Create house history step by step wtih validation using UI |  | 3 | 150 | 139 | Collaboration | 0 | 11
14 | Retrieve Deed from the database |  | 3 | 8 | 8 | Collaboration | 2 | 8
|  |  | Planned Total | 621 | 416 | Actual Total | 110 | 164

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Title Search Team
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Brandon Toups | 11 | 9 | 9 | 8,9,10 | 40 | 0 | 0 | 7 | 7 | 2 | 2 | 6 | 6 | 15 | 15
| Justin Greenfield | 2019-08-09 | 2019-04-05 | 2019-04-05 | 2019-04-05 | 20 | 0 | 0 | 4 | 8 | 3 | 3 | 4 | 4 | 11 | 15
| Jay Patel | 1, 2, 3, 6, 11 | 1, 2. 3. 6, 11 | 1, 2, 3, 6, 11 | 1, 2, 3, 6, 11 | 60 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2
| Mina Narayanan | 1, 2, 3, | 1 | 2019-01-03 | 2019-01-03 | 20 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 5 | 5
| AJ Hancher | 2,7,1 | 7 | 1,2,7 | 1,2,7 | 10 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 3 | 3
[5 empty] | Totals | 150 | 3 | 3 | 16 | 20 | 5 | 5 | 12 | 12 | 36 | 40
Planned Product Hours < 80% Planned Team Hours.
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| Validation UI now shows errors if the user submits invalid values for any of the fields in the validation menu. | [6 empty] | Have a prototype of UI that allows the user to validate the entity extraction by the NLU. Integrate all parts of the project together using the new decoupled architecture. Work on having combined house history.
| Obstacles encountered since last status report: | [6 empty] | Notes:
Sponsor did not like the project architecture up to this point. So we had to revamp the architecture to be strictly OOP with a more decoupled design. Also had to transfer all the IMBCloud architecture onto our sponsor's account.
Risks facing the project:
Failure to complete all necessary portions of the project. We are unsure of the project scope in regards to the WarrantyDeed recursive search as well as the TrustDeed recursive search. Waranty deed should be possible, but Trust deed will have added complexity unlike the Warranty deeds. Lack of standardization in the deeds

## Justin Greenfield
COMP4710 Status Report - Member Timesheet
Project Name: |  | TitleSearch
Member: |  | Justin Greenfield
Week Ending: |  | 2019-04-08
Cycle: |  | CYCLE 2
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | Completed presentation, worked on demo
Date: | 2019-04-02 | Result: | Cycle 2 Presentation complete, demo complete
Hours Worked: | 2.5 | Problems encountered: | N/A
Day: | Thursday | Task(s) performed: | Tested new WKS model, created ParseJSON, DeleteDuplicates, and PopulateDeed methods
Date: | 2019-04-04 | Result: | Task completed
Hours Worked: | 3 | Problems encountered: | Had to make design decision of whether to convert JSON to Java object using GSON library or use custom ParseJSON method to extract and assign entities
Day: | Sunday | Task(s) performed: | Completed ParseJSON, DeleteDuplicates, and PopulateDeeds methods, consolidated 3 methods into single PopulateDeed method
Date: | 2019-04-07 | Result: | Task Completed
Hours Worked: | 2.5 | Problems encountered: | Deciding whether it was better to use 3 methods in cohesion or one consolidated "big" method
Day: | Tuesday | Task(s) performed: | Tested fully-functional nluAPI, tested fully-funcitonal populateDeed method()
Date: | 2019-04-09 | Result: | Completed crude testing with screenshots of output
Hours Worked: | 1 | Problems encountered: | Issues where entities are mispelled within the Deeds --> ValidationUI solves this problem
Day: | Monday | Task(s) performed: | Tested nluAPI for extraction and variable assignment, refactored WarrantyDeed, WarrantyDeedManager, and NaturalLanguageUnderstandingAPI
Date: | 2019-04-01 | Result: | Task Completed
Hours Worked: | 1 | Problems encountered: | No problems but some fields within our object had to be changed from single String values to String arrays (in order to hold multiple values)

## Brandon Toups
COMP4710 Status Report - Member Timesheet
Project Name: |  | Title Search
Member: |  | Brandon Toups
Week Ending: |  | 2019-04-08
Cycle: |  | CYCLE 1
Team Member Work Summary
Monday | Tuesday | Task(s) performed:
Date: | 2019-04-02 | Result:
Hours Worked: |  | Problems encountered:
Day: | Wednesday | Task(s) performed: | - Move everything into sponsor's IBM Cloud so that everything exists in one place rather than each person's personal cloud. This includes re-uploading and retraining on Trey's new instance. (2) - Do some more document gathering and data cleaning (2)
Date: | 2019-04-03 | Result: | - Successful reupload and retrain
Hours Worked: | 4 | Problems encountered:
Day: | Thursday | Task(s) performed: | - More document gathering and training based on the book an page number (1) - IBM Cloud testing and figuring out the NLU api calls. (4)
Date: | 2019-04-04 | Result:
Hours Worked: | 5 | Problems encountered: | - IBM Documentation is out of date. Tutorial is out of date as well. Still referenced deprecated username and password combination for auth. Had to spend few hours figuring out the proper way to do this
Day: | Friday | Task(s) performed: | - Testing the nlu api calls for proper extraction (2) - Finishing book and page number and grantor/gratee training for a suitable amount (2)
Date: | 2019-04-05 | Result: | - At this point, we are getting proper extractions we can handle accuracy user side. Training past this is all just how perfect we can get it. Hovering around .75 extraction accuracy when split and .65 when combined.
Hours Worked: | 4 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-04-06 | Result:
Hours Worked: |  | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-04-07 | Result:
Hours Worked: |  | Problems encountered:
Day: | Monday | Task(s) performed: | - Writing documentation for if this becomes a continuation project. Used markdown. Outlined process for gathering docs and training WKS because the online outline is confusing and leaves out stuff or vaguely refrences certain things that end up being the parts that took up the most amount of time. Also incorporates our bespoke process.
Date: | 2019-04-08 | Result:
Hours Worked: | 2 | Problems encountered:

## Jay Patel
COMP4710 Status Report - Member Timesheet
Project Name: |  | TitleSearch
Member: |  | Jay Patel
Week Ending: |  | 2019-04-08
Cycle: |  | CYCLE 1
Team Member Work Summary
Monday | Tuesday | Task(s) performed:
Date: | 2019-04-02 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed: | Minor refactoring of the TitleSearchManager class to handle the process of creating the house history using the UI. Also implemented showing an error in the UI when a WarrantyDeed validation sent by the user fails to meet certain requirements.
Date: | 2019-04-03 | Result: | The UI now shows errors if the user submits invalid values for the fields in the validation menu.
Hours Worked: | 2 | Problems encountered: | None
Day: | Thursday | Task(s) performed:
Date: | 2019-04-04 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2019-04-05 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-04-06 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-04-07 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-04-08 | Result:
Hours Worked: | 0 | Problems encountered:

## Mina Narayanan
COMP4710 Status Report - Member Timesheet
Project Name: |  | TitleSearch
Member: |  | Mina Narayanan
Week Ending: |  | 2019-04-08
Cycle: |  | CYCLE 3
Team Member Work Summary
Monday | Tuesday | Task(s) performed: | Debugged implementation of TitleSearcherAPI, which now returns an ArrayList of WarrantyDeed objects that match the user's search
Date: | 2019-04-02 | Result: | Slightly less buggy version of TitleSearcherAPI
Hours Worked: | 2 | Problems encountered:
Day: | Wednesday | Task(s) performed: | Completed new implementation of TitleSearcherAPI, which now allows user to search by first name and last name
Date: | 2019-04-03 | Result: | Final TitleSearcherAPI class
Hours Worked: | 2 | Problems encountered:
Day: | Thursday | Task(s) performed: | N/A
Date: | 2019-04-04 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed: | Renamed WarrantyDeeds to more accurately reflect user search
Date: | 2019-04-05 | Result: | WarrantyDeeds that are now named either firstName_lastName_# or bookNo_PageNo_#
Hours Worked: | 1 | Problems encountered:
Day: | Saturday | Task(s) performed: | N/A
Date: | 2019-04-06 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | N/A
Date: | 2019-04-07 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed: | N/A
Date: | 2019-04-08 | Result:
Hours Worked: | 0 | Problems encountered:

## AJ Hancher
COMP4710 Status Report - Member Timesheet
Project Name: |  | TitleSearch
Member: |  | AJ Hancher
Week Ending: |  | 2019-04-08
Cycle: |  | CYCLE 1
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | Finshed the database to allow it to store warranty deed objects
Date: | 2019-04-02 | Result: | Finished the database for warrantydeeds
Hours Worked: | 2 | Problems encountered:
Day: | Wednesday | Task(s) performed: | Created a method that gets the warranty deeds based on either ID, Name, or date
Date: | 2019-04-03 | Result: | Finished the get methods for the warranty deed
Hours Worked: | 1 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2019-04-04 | Result:
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed:
Date: | 2019-04-05 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed: | N/A
Date: | 2019-04-06 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed:
Date: | 2019-04-07 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-04-08 | Result:
Hours Worked: | 0 | Problems encountered: