## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | TitleSearch | [6 empty] | Completed | 1
| Team Members: | Mina, Justin, Brandon, Jay, AJ | [6 empty] | Discarded | 2
| Date: | 2019-04-08 | Cycle: | 3 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | People seeking to purchase real estate must perform a “title search” to verify that none of the previous owners of the property over the past 40+ years still have any outstanding loans or liens on the residence. This process is expensive in terms of time and money. The aim of our software is to use artificial intelligence to automate this search, allowing people to bypass lawyers in lieu of quickly finding out property information for themselves. | [6 empty] | In Review
Unstarted
| Cycle Intent: | The intent of Cycle 3 is to create a robust, end-to-end design for searching for warranty deeds by book number and page number as well as first name and last name.
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Receive PDF of entered WD book and page number |  | 1 | 40 | 20 | Completed | 42 | 66
2 | Convert PDF into text document |  | 1 | 2 | 0 | Completed | 2 | 2
3 | Enter WD book and page number to get report on house |  | 1 | 3 | 3 | Collaboration | 5 | 5
4 | NLU - Analyze Text |  | 1 | 10 | 8 | Completed | 8 | 8
5 | NLU - Extract Grantor and Grantee from Waranty Deed |  | 2 | 10 | 2 | Completed | 3 | 3
6 | Search any term in document processed by Discovery |  | 1 | 15 | 0 | Completed | 20 | 20
7 | Store deeds in a functional database |  | 1 | 10 | 10 | Completed | 2 | 2
8 | Have Watson analyze types and subtypes relationships- Annotations |  | 1 | 10 | 3 | Completed | 3 | 3
9 | Watson learn how to automatically recognize Grantors and Grantees |  | 1 | 20 | 23 | In Review | 23 | 26
10 | Watson to be able to understand domain specific knowledge (Relationships) |  | 2 | 3 | 0 | Discarded | 0 | 0
11 | Generate report of the history of a house using warranty deeds. |  | 3 | 200 | 200 | Collaboration | 0 | 0
12 | Validation of NLU entity extraction by means of UI input boxes |  | 2 | 140 | 0 | Completed | 0 | 10
13 | Create house history step by step wtih validation using UI |  | 3 | 150 | 139 | Collaboration | 0 | 11
14 | Retrieve Deed from the database |  | 3 | 8 | 8 | Collaboration | 4 | 8
|  |  | Planned Total | 621 | 416 | Actual Total | 112 | 164

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Title Search Team
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Brandon Toups | 11 | 9 | 9 | 8,9,10 | 40 | 0 | 0 | 3 | 6 | 0 | 2 | 0 | 6 | 3 | 14
| Justin Greenfield | 2019-08-09 | 2019-04-05 | 2019-04-05 | 2019-04-05 | 20 | 1 | 0 | 1.5 | 8 | 0 | 3 | 1 | 4 | 3.5 | 15
| Jay Patel | 1, 2, 3, 6, 11 | 1, 2. 3. 6, 11 | 1, 2, 3, 6, 11 | 1, 2, 3, 6, 11 | 60 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 3
| Mina Narayanan | 1, 2, 3, | 1 | 2019-01-03 | 2019-01-03 | 20 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 5 | 5
| AJ Hancher | 2,7,1 | 7 | 1,2,7 | 1,2,7 | 10 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 3 | 3
[5 empty] | Totals | 150 | 3 | 3 | 9.5 | 19 | 0 | 5 | 3 | 13 | 15.5 | 40
Planned Product Hours < 80% Planned Team Hours.
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| Validation UI now shows errors if the user submits invalid values for any of the fields in the validation menu. | [6 empty] | Have a prototype of UI that allows the user to validate the entity extraction by the NLU. Integrate all parts of the project together using the new decoupled architecture. Work on having combined house history.
| Obstacles encountered since last status report: | [6 empty] | Notes:
Sponsor did not like the project architecture up to this point. So we had to revamp the architecture to be strictly OOP with a more decoupled design. Also had to transfer all the IMBCloud architecture onto our sponsor's account.
Risks facing the project:
Failure to complete all necessary portions of the project. We are unsure of the project scope in regards to the WarrantyDeed recursive search as well as the TrustDeed recursive search. Waranty deed should be possible, but Trust deed will have added complexity unlike the Warranty deeds. Lack of standardization in the deeds

## Justin Greenfield
COMP4710 Status Report - Member Timesheet
Project Name: |  | TitleSearch
Member: |  | Justin Greenfield
Week Ending: |  | 2019-04-15
Cycle: |  | CYCLE 3
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | Tested extraction functionality, changed book and page number back to string and discussed with team which extracted values we want to take
Date: | 2019-04-09 | Result: | task complete
Hours Worked: | 1.5 | Problems encountered: | some OutOfBoundsException errors for different ways of extracting values
Day: | Wednesday | Task(s) performed: | Met with group to consolidate latest files, discuss design, and setup unit testing
Date: | 2019-04-10 | Result: | Jay has the unit testing setup on local computer
Hours Worked: | 1 | Problems encountered: | figuring out which book/page number we should take from extracted values
Day: | Thursday | Task(s) performed: | N/A
Date: | 2019-04-11 | Result: | N/A
Hours Worked: |  | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | N/A
Date: | 2019-04-14 | Result: | N/A
Hours Worked: |  | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | More entity extraction tampering
Date: | 2019-04-15 | Result: | Tampering completed
Hours Worked: | 1 | Problems encountered: | None

## Brandon Toups
COMP4710 Status Report - Member Timesheet
Project Name: |  | Title Search
Member: |  | Brandon Toups
Week Ending: |  | 2019-04-08
Cycle: |  | CYCLE 1
Team Member Work Summary
Monday | Tuesday | Task(s) performed:
Date: | 2019-04-09 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2019-04-10 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2019-04-11 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2019-04-12 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-04-13 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | - Finish wks documentation
Date: | 2019-04-14 | Result:
Hours Worked: | 1 | Problems encountered:
Day: | Monday | Task(s) performed: | - About finished document extraction documentation - Debug virtualenv setup for document extraction. had to learn about pipenv
Date: | 2019-04-15 | Result: | - Pipenv successfully set up virtual env necessary - Users should be able to pick up where we left off
Hours Worked: | 2 | Problems encountered: | - At some point the extraction was working but only for specific instances I could not figure out why.

## Jay Patel
COMP4710 Status Report - Member Timesheet
Project Name: |  | TitleSearch
Member: |  | Jay Patel
Week Ending: |  | 2019-04-08
Cycle: |  | CYCLE 1
Team Member Work Summary
Monday | Tuesday | Task(s) performed:
Date: | 2019-04-09 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed: | Integrated the updated code base from other members into the integrated github repository.
Date: | 2019-04-10 | Result: | Github repository contains the most up-to-date integrated codebase.
Hours Worked: | 1 | Problems encountered: | None
Day: | Thursday | Task(s) performed:
Date: | 2019-04-11 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2019-04-12 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-04-13 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-04-14 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-04-15 | Result:
Hours Worked: | 0 | Problems encountered:

## Mina Narayanan
COMP4710 Status Report - Member Timesheet
Project Name: |  | TitleSearch
Member: |  | Mina Narayanan
Week Ending: |  | 2019-04-15
Cycle: |  | CYCLE 3
Team Member Work Summary
Monday | Tuesday | Task(s) performed: | N/A
Date: | 2019-04-09 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed: | N/A
Date: | 2019-04-10 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed: | N/A
Date: | 2019-04-11 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed: | Began implementing unit tests for BeautifulSoupAPI.py
Date: | 2019-04-12 | Result: | Unit test stubs
Hours Worked: | 2 | Problems encountered: | None
Day: | Saturday | Task(s) performed: | N/A
Date: | 2019-04-13 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | N/A
Date: | 2019-04-14 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed: | Built WarrantyDeed object in BeautifulSoupAPI instead of TitleSearcherManager to try and fix Jay's problem of not being able to download warranty deeds
Date: | 2019-04-15 | Result: | Buggy implementation - PythonInterpreter unable to find BeautifulSoupAPI.py
Hours Worked: | 4 | Problems encountered: | Jython can be unwieldy and doesn't work with Python3

## AJ Hancher
COMP4710 Status Report - Member Timesheet
Project Name: |  | TitleSearch
Member: |  | AJ Hancher
Week Ending: |  | 2019-04-15
Cycle: |  | CYCLE 3
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | Continued work on allowing for trust deeds to be stored
Date: | 2019-04-09 | Result: | Almost have a finished product for trust deeds
Hours Worked: | 2 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2019-04-10 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2019-04-11 | Result:
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed:
Date: | 2019-04-12 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed: | N/A
Date: | 2019-04-13 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed:
Date: | 2019-04-14 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-04-15 | Result:
Hours Worked: | 0 | Problems encountered: