## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | TitleSearch | [6 empty] | Completed | 1
| Team Members: | Mina, Justin, Brandon, Jay, AJ | [6 empty] | Discarded | 2
| Date: | 2019-02-26 | Cycle: | 1 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | People seeking to purchase real estate must perform a “title search” to verify that none of the previous owners of the property over the past 40+ years still have any outstanding loans or liens on the residence. This process is expensive in terms of time and money. The aim of our software is to use artificial intelligence to automate this search, allowing people to bypass lawyers in lieu of quickly finding out property information for themselves. | [6 empty] | In Review
Unstarted
| Cycle Intent: | The intent of Cycle 1 is to explore how to work with the technologies provided. Since we are the first group to work on this project, we are given a lot of freedom in choosing how to begin, design, and implement it. Because of this, the majority of this cycle is experimenting with the various technologies and suggestions made by the sponsor in order to fully understand how we will implement this.
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Receive PDF of entered WD book and page number |  | 1 | 40 | 20 | Completed | 42 | 66
2 | Convert PDF into text document |  | 1 | 2 | 0 | Completed | 2 | 2
3 | Enter WD book and page number to get report on house |  | 1 | 3 | 3 | Collaboration | 5 | 5
4 | NLU - Analyze Text |  | 1 | 10 | 8 | Completed | 8 | 8
5 | NLU - Extract Grantor and Grantee from Waranty Deed |  | 2 | 10 | 2 | Completed | 3 | 3
6 | Search any term in document processed by Discovery |  | 1 | 15 | 0 | Completed | 20 | 20
7 | Store deeds in a functional database |  | 1 | 10 | 10 | Collaboration | 2 | 2
8 | Have Watson analyze types and subtypes relationships- Annotations |  | 1 | 10 | 3 | Collaboration | 3 | 3
9 | Watson learn how to automatically recognize Grantors and Grantees |  | 1 | 3 | 3 | Collaboration | 3 | 3
10 | Watson to be able to understand domain specific knowledge (Relationships) |  | 2 | 3 | 0 | Adversarial | 0 | 0
11 | Generate report of the history of a house using warranty deeds. |  | 3 | 200 | 0 | Collaboration | 0 | 0
12 | Validation of NLU entity extraction by means of UI input boxes |  | 2 | 140 | 10 | Unstarted
13 | Create house history step by step wtih validation using UI |  | 2 | 150 | 0 | Unstarted
|  |  | Planned Total | 596 | 59 | Actual Total | 88 | 112

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Title Search Team
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Brandon Toups | 5 | 8,9,10 | 8,9,10 | 8,9,10 | 25 | 0 | 0 |  | 7 | 6 | 7 | 5 | 12 | 11 | 26
| Justin Greenfield | 2019-08-09 | 2019-04-05 | 2019-04-05 | 2019-04-05 | 20 | 0 | 0 | 4 | 8 | 3 | 3 | 4 | 4 | 11 | 15
| Jay Patel | 1, 2, 3, 6, 11 | 1, 2. 3. 6, 11 | 1, 2, 3, 6, 11 | 1, 2, 3, 6, 11 | 60 | 0 | 0 | 5 | 41 | 4 | 5 | 0 | 0 | 9 | 46
| Mina Narayanan | 1, 2, 3, | 1 | 2019-01-03 | 2019-01-03 | 20 | 3 | 3 | 4 | 4 | 1 | 1 | 4 | 4 | 12 | 12
| AJ Hancher | 2,7,1 | 7 | 1,2,7 | 1,2,7 | 30 | 0 | 0 | 3 | 6 | 1 | 1 | 3 | 6 | 7 | 14
[5 empty] | Totals | 155 | 3 | 3 | 16 | 66 | 15 | 17 | 16 | 26 | 50 | 113
Planned Product Hours < 80% Planned Team Hours.
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| Creating a more decoupled design for the architecture. | [6 empty] | Have a prototype of UI that allows the user to validate the entity extraction by the NLU. Integrate all parts of the project together using the new decoupled architecture.
| Obstacles encountered since last status report: | [6 empty] | Notes:
Sponsor did not like the project architecture up to this point. So we had to revamp the architecture to be strictly OOP with a more decoupled design.
Risks facing the project:
Failure to complete all necessary portions of the project. We are unsure of the project scope in regards to the WarrantyDeed recursive search as well as the TrustDeed recursive search. Waranty deed should be possible, but Trust deed will have added complexity unlike the Warranty deeds. Lack of standardization in the deeds

## Member 1 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | TitleSearch
Member: |  | Justin Greenfield
Week Ending: |  | 2019-02-25
Cycle: |  | CYCLE 2
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | Met with client to discuss project architecture and additional specifications
Date: | 2019-02-19 | Result: | Changed project architecture drastically, taking Object Oriented approach
Hours Worked: | 2 | Problems encountered: | Had to edit a lot of code
Day: | Wednesday | Task(s) performed: | Refactored and edited NLU API, began drafting and researching transition to object-oriented approach
Date: | 2019-02-20 | Result: | Task Ccompleted
Hours Worked: | 2 | Problems encountered: | Problems passing variables from class to class, figured out
Day: | Thursday | Task(s) performed: | wrote shell-code for new WarrantyDeed and WarrantyDeedManager() classes, filled out getter methods for WarrantyDeed Class
Date: | 2019-02-24 | Result: | Task Completed
Hours Worked: | 3 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Met with group members to work on Class Sequence diagrams for client
Date: | 2019-02-24 | Result: | Completed sequence diagrams for a few classes
Hours Worked: | 3 | Problems encountered: | some sequence diagram confusion
Day: | Monday | Task(s) performed: | met with client and discussed sequence diagrams, made changes to our architecture and discussed hashing methods
Date: | 2019-02-25 | Result: | Task Completed, refactored sequence diagram
Hours Worked: | 1 | Problems encountered: | N/A

## Member 2 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Title Search
Member: |  | Brandon Toups
Week Ending: |  | 2019-02-12
Cycle: |  | CYCLE 1
Team Member Work Summary
Monday | Tuesday | Task(s) performed: | - Meeting with sponsor to discuss OOP
Date: | 2019-02-19 | Result: | Success
Hours Worked: | 3 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2019-02-20 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed: | - Reviewing documentation and requirements specifications from sponsor. - Outlining approach to downloading WDs in bulk
Date: | 2019-02-21 | Result: | Jay's UI will allow me to approach bulk downlaod more efficiently and effectively.
Hours Worked: | 1 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2019-02-22 | Result:
Hours Worked: |  | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-02-23 | Result:
Hours Worked: |  | Problems encountered:
Day: | Sunday | Task(s) performed: | - Design documentation and system sequence diagram collaboration with Jay and Justin.
Date: | 2019-02-24 | Result: | - Successful creation of SSQ diagrams
Hours Worked: | 3 | Problems encountered:
Day: | Monday | Task(s) performed: | - Working on building actual classes in alignment with OOP approach sponsor is suggesting. Need - Meeting with sponsor to go over this in detail, as well as other pressing questions
Date: | 2019-02-25 | Result:
Hours Worked: | 4 | Problems encountered:

## Member 3 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | TitleSearch
Member: |  | Jay Patel
Week Ending: |  | 2026-02-18
Cycle: |  | CYCLE 1
Team Member Work Summary
Monday | Tuesday | Task(s) performed: | Met with sponsor to show him the current status of the project as well as receive input from him on the project design.
Date: | 2019-02-19 | Result: | Success.
Hours Worked: | 3 | Problems encountered: | None.
Day: | Wednesday | Task(s) performed:
Date: | 2019-02-20 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2019-02-21 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed: | Started to work on the sequence diagrams requested by the sponsor to show the project architecture.
Date: | 2019-02-22 | Result: | Success.
Hours Worked: | 2 | Problems encountered: | None.
Day: | Saturday | Task(s) performed:
Date: | 2019-02-23 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | Finished initial sequence diagrams to show to our sponsor for the meeting on Monday.
Date: | 2019-02-24 | Result: | Success.
Hours Worked: | 3 | Problems encountered: | None.
Day: | Monday | Task(s) performed: | Met with sponsor on WebEx to show him the sequence diagrams and receive input.
Date: | 2019-02-25 | Result: | Success, received feedback about changes to the sequence diagrams.
Hours Worked: | 1 | Problems encountered: | None.

## Member 4 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | TitleSearch
Member: |  | Mina Narayanan
Week Ending: |  | 2019-02-26
Cycle: |  | CYCLE 1
Team Member Work Summary
Monday | Tuesday | Task(s) performed: | Met with our sponsor, Trey, to update him on our progress and get a better understanding of how our individual components tie together
Date: | 2019-02-19 | Result: | Clear direction for project
Hours Worked: | 3 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | N/A
Date: | 2019-02-20 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Thursday | Task(s) performed: | N/A
Date: | 2019-02-21 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Worked on getting Non-Indexed Documents to download correctly
Date: | 2019-02-22 | Result: | Refactored API image download code
Hours Worked: | 4 | Problems encountered: | Images did not download correctly for some reason, wrong http request perhaps?
Day: | Saturday | Task(s) performed: | Worked on getting Non-Indexed Documents to download correctly
Date: | 2019-02-23 | Result: | Non-indexed documents are downloaded correctly in the appropriate directory
Hours Worked: | 5 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | N/A
Date: | 2019-02-24 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | N/A
Date: | 2019-02-25 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A

## Member 5 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | TitleSearch
Member: |  | AJ Hancher
Week Ending: |  | 2019-02-12
Cycle: |  | CYCLE 1
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | Met with our sponsor in person to specify what he wants us to do
Date: | 2019-02-19 | Result: | Great Meeting that layed out our groundwork and how we are going to change to OOP
Hours Worked: | 2 | Problems encountered:
Day: | Wednesday | Task(s) performed: | Researched API for MongoDB through IBM Cloud
Date: | 2019-02-20 | Result: | Started implementing the API's
Hours Worked: | 1 | Problems encountered:
Day: | Thursday | Task(s) performed: | Error correcting on the API's.
Date: | 2019-02-21 | Result: | Still can't get it to work properly
Hours Worked: | 2 | Problems encountered: | N/A
Day: | Friday | Task(s) performed:
Date: | 2019-02-22 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed: | N/A
Date: | 2019-02-23 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed:
Date: | 2019-02-24 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed: | Started creating the Sequence Diagrams for the Database functions
Date: | 2019-02-25 | Result: | Work in progress
Hours Worked: | 1 | Problems encountered: