## _Boilerplate
Team Member Work Summary
Monday | Tuesday | Task(s) performed:
Date: | 2019-02-26 | Result:
Hours Worked: |  | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2019-02-27 | Result:
Hours Worked: |  | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2019-02-28 | Result:
Hours Worked: |  | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2019-03-01 | Result:
Hours Worked: |  | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-03-02 | Result:
Hours Worked: |  | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-03-03 | Result:
Hours Worked: |  | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-03-04 | Result:
Hours Worked: |  | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-03-05 | Result:
Hours Worked: |  | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2019-03-06 | Result:
Hours Worked: |  | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2019-03-07 | Result:
Hours Worked: |  | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2019-03-08 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-03-09 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-03-10 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-03-11 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-03-12 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2019-03-13 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2019-03-14 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2019-03-15 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-03-16 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | Met with Jay to discuss how I saw the database manager API's being implemented
Date: | 2019-03-17 | Result: | Started work on the apis
Hours Worked: | 3 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-03-18 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-03-19 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2019-03-20 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed: | Continued the work on the database manager APi
Date: | 2019-03-21 | Result: | Got a model that can be used to test
Hours Worked: | 2 | Problems encountered:
Day: | Friday | Task(s) performed: | Met with our sponor
Date: | 2019-03-22 | Result: | Laid out a plan for the rest of the semester
Hours Worked: | 1 | Problems encountered:
Day: | Saturday | Task(s) performed: | Worked on integrating the database with the other parts of the project
Date: | 2019-03-23 | Result: | Still in progress
Hours Worked: | 6 | Problems encountered: | Connecting the database to a cloud service instance
Day: | Sunday | Task(s) performed: | Set up a meeting with our sponsor for help with connecitng the database to ibm cloud
Date: | 2019-03-24 | Result: | Meeting set up for 3/23/19]
Hours Worked: | 1 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-03-25 | Result:
Hours Worked: | 0 | Problems encountered:

## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | TitleSearch | [6 empty] | Completed | 1
| Team Members: | Mina, Justin, Brandon, Jay, AJ | [6 empty] | Discarded | 2
| Date: | 2019-03-26 | Cycle: | 2 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | People seeking to purchase real estate must perform a “title search” to verify that none of the previous owners of the property over the past 40+ years still have any outstanding loans or liens on the residence. This process is expensive in terms of time and money. The aim of our software is to use artificial intelligence to automate this search, allowing people to bypass lawyers in lieu of quickly finding out property information for themselves. | [6 empty] | In Review
Unstarted
| Cycle Intent: | The intent of Cycle 2 is to implement the architectural changes finalized in Cycle 1. Our primary objective is to integrate members' individual components and ensure that the exchange of information between classes is easy and the information itself is represented appropriately.
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Receive PDF of entered WD book and page number |  | 1 | 40 | 20 | Completed | 42 | 66
2 | Convert PDF into text document |  | 1 | 2 | 0 | Completed | 2 | 2
3 | Enter WD book and page number to get report on house |  | 1 | 3 | 3 | Completed | 5 | 5
4 | NLU - Analyze Text |  | 1 | 10 | 8 | Completed | 8 | 8
5 | NLU - Extract Grantor and Grantee from Waranty Deed |  | 2 | 10 | 2 | Completed | 3 | 3
6 | Search any term in document processed by Discovery |  | 1 | 15 | 0 | Completed | 20 | 20
7 | Store deeds in a functional database |  | 1 | 10 | 10 | Collaboration | 2 | 2
8 | Have Watson analyze types and subtypes relationships- Annotations |  | 1 | 10 | 3 | Collaboration | 3 | 3
9 | Watson learn how to automatically recognize Grantors and Grantees |  | 1 | 20 | 23 | In Review | 23 | 26
10 | Watson to be able to understand domain specific knowledge (Relationships) |  | 2 | 3 | 0 | Discarded | 0 | 0
11 | Generate report of the history of a house using warranty deeds. |  | 3 | 200 | 0 | Collaboration | 0 | 0
12 | Validation of NLU entity extraction by means of UI input boxes |  | 2 | 140 | 10 | Collaboration | 10 | 10
13 | Create house history step by step wtih validation using UI |  | 2 | 150 | 150 | Collaboration | 11 | 11
14 | Retrieve Deed from the database |  | 2 | 8 |  | Unstarted
|  |  | Planned Total | 621 | 229 | Actual Total | 129 | 156

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Title Search Team
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Brandon Toups | 5 | 8,9,10 | 8,9,10 | 8,9,10 | 25 | 0 | 0 | 8 | 8 | 2 | 2 | 23 | 23 | 33 | 33
| Justin Greenfield | 2019-08-09 | 2019-04-05 | 2019-04-05 | 2019-04-05 | 20 | 0 | 0 | 4 | 8 | 3 | 3 | 4 | 4 | 11 | 15
| Jay Patel | 1, 2, 3, 6, 11 | 1, 2. 3. 6, 11 | 1, 2, 3, 6, 11 | 1, 2, 3, 6, 11 | 30 | 0 | 0 | 10 | 10 | 2 | 2 | 11 | 11 | 23 | 23
| Mina Narayanan | 1, 2, 3, | 1 | 2019-01-03 | 2019-01-03 | 30 | 6 | 6 | 2 | 2 | 1 | 1 | 2 | 2 | 11 | 11
| AJ Hancher | 2,7,1 | 2019-07-14 | 1,2,7 | 1,2,7 | 30 | 0 | 0 | 3 | 6 | 1 | 1 | 6 | 10 | 10 | 20
[5 empty] | Totals | 135 | 6 | 6 | 27 | 34 | 9 | 9 | 46 | 50 | 88 | 102
Planned Product Hours < 80% Planned Team Hours.
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| Creating a more decoupled design for the architecture. Created UIs for the house history report and for validating a warranty deed represented by a WarrantyDeed object. | [6 empty] | Integrate all parts of the project together using the new decoupled architecture. Have the functionality to search for a warranty deed and initiate the house history report step by step.
| Obstacles encountered since last status report: | [6 empty] | Notes:
Sponsor did not like the project architecture up to this point. So we had to revamp the architecture to be strictly OOP with a more decoupled design.
Risks facing the project:
Failure to complete all necessary portions of the project. We are unsure of the project scope in regards to the WarrantyDeed recursive search as well as the TrustDeed recursive search. Waranty deed should be possible, but Trust deed will have added complexity unlike the Warranty deeds. Lack of standardization in the deeds

## Justin Greenfield
COMP4710 Status Report - Member Timesheet
Project Name: |  | TitleSearch
Member: |  | Justin Greenfield
Week Ending: |  | 2019-03-25
Cycle: |  | CYCLE 2
Team Member Work Summary
Day: | Wednesday | Task(s) performed: | WLK Model Testing, WarrantyDeed and NaturalLanguageUnderstandingAPI refactors
Date: | 2019-03-20 | Result: | Refactored class methods, cleaned up some junk
Hours Worked: | 2 | Problems encountered: | Had to edit a lot of code
Day: | Thursday | Task(s) performed: | WLK Model Testing and Troubleshooting
Date: | 2019-03-21 | Result: | Task Ccompleted
Hours Worked: | 1 | Problems encountered: | Still some issues with entity extraction (Grantor, Grantee)
Day: | Friday | Task(s) performed: | Meeting with Client, GSON Library research and implementation
Date: | 2019-03-22 | Result: | Task Completed - Planning for full system run through by end of week
Hours Worked: | 1.5 | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | WarrantyDeedManager class creation and more GSON research/implementation
Date: | 2019-03-25 | Result: | Have a good rough draft of WarrantyDeedManager class, need to consolidate with team members
Hours Worked: | 2 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Meeting with Client to discuss deliverables going forward
Date: | 2019-03-06 | Result: | Completed
Hours Worked: | 1 | Problems encountered: | N/A
Day: | Thursday | Task(s) performed: | Creation of WarrantyDeed class (information class)
Date: | 2019-03-07 | Result: | Completed - Support from Jay helped a lot
Hours Worked: | 2 | Problems encountered: | Changes in which member-variables make up the Object
Day: | Monday | Task(s) performed: | Changes in NaturalLanguageUnderstandingAPI, updating parameters and refactoring code
Date: | 2019-03-18 | Result: | Completed
Hours Worked: |  | Problems encountered: | some slight confusion with which parameter the nlu api should take in
Day: | Wednesday | Task(s) performed: | Initial WLK + NLU testing, creation of test.java method that creates instance of NLUAPI and passes through WarrantyDeed text
Date: | 2019-03-20 | Result: | Completed
Hours Worked: |  | Problems encountered: | test failed -- still some issues with entity extraction
1hr | Tuesday, April 9th |  | Tested fully-functional nluAPI, tested fully-funcitonal populateDeed method()

## Brandon Toups
COMP4710 Status Report - Member Timesheet
Project Name: |  | Title Search
Member: |  | Brandon Toups
Week Ending: |  | 2019-03-26
Cycle: |  | CYCLE 2
Team Member Work Summary
Monday | Tuesday | Task(s) performed: | - Architectural planning of the work going further, including discussions of the UI that will be implemented
Date: | 2019-02-26 | Result: | Success
Hours Worked: | 2 | Problems encountered:
Day: | Wednesday | Task(s) performed: | - WKS experimentation with entities - Quick meeting to discuss next steps
Date: | 2019-02-27 | Result: | success
Hours Worked: | 2 | Problems encountered:
Day: | Thursday | Task(s) performed: | - Integration of repos and branches into monorepo. - Preparing for UI prototype for monday - Gathering bulk pdfs for training WKS - Inputting pdfs into Jay's frontend. Need to now use his other website for generating text, and then saving into .txt locally for input into WKS
Date: | 2019-02-28 | Result: | success, next step is downloading the text
Hours Worked: | 3 | Problems encountered: | Had to use Jay's website for this, but required a little modification for speeding up process
Day: | Friday | Task(s) performed:
Date: | 2019-03-01 | Result:
Hours Worked: |  | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-03-02 | Result:
Hours Worked: |  | Problems encountered:
Day: | Sunday | Task(s) performed: | - Presentation practice - Typing up finishing cycle 1 deliverables
Date: | 2019-03-03 | Result:
Hours Worked: | 2 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-03-04 | Result:
Hours Worked: |  | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-03-05 | Result:
Hours Worked: |  | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2019-03-06 | Result:
Hours Worked: |  | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2019-03-07 | Result:
Hours Worked: |  | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2019-03-08 | Result:
Hours Worked: |  | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-03-09 | Result:
Hours Worked: |  | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-03-10 | Result:
Hours Worked: |  | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-03-11 | Result:
Hours Worked: |  | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-03-12 | Result:
Hours Worked: |  | Problems encountered:
Day: | Wednesday | Task(s) performed: | - Write JS function for helping to automate downloading .txt files from /Query.jsp and /FindFile. Pushed to github - This is more of a scalability concern - Format and boilerplate creation for 3 week long status report
Date: | 2019-03-13 | Result:
Hours Worked: | 5 | Problems encountered: | - Extraneous space on end of UI's filename was 30 min debugging - Not reloading page to delete/clear globals was 1 hour debugging - Have never written javascript or devtools before so this was new. - Realized ~10/50 were handwritten warranty deeds/cursive. Need more to make more accurate
Day: | Thursday | Task(s) performed:
Date: | 2019-03-14 | Result:
Hours Worked: |  | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2019-03-15 | Result:
Hours Worked: |  | Problems encountered:
Day: | Saturday | Task(s) performed: | - WKS revamp. Had to completely reconfigure how everything was set up - Because of this, had to re-annotate WKS on the initial sets - Training and evaluation done on intiial set =0% - Training and evaluation done on second and first set at same time =0% - Training and evaluation done on second set only =48% - Training and evaluation done on third set only =
Date: | 2019-03-16 | Result: | - Much more intuitive WKS setups/layout/file structure and annotation tasking. - Everything can now be delegated if need be. - Due to first iteration, focusing on grantor/grantee as opposed to previous approach to annotating
Hours Worked: | 7 | Problems encountered: | - Initial document set was jumbled due to staggered upload. This led to confusion with which sets associated with which train. - Therefore, I had to delete in order to bulk upload (leading to consolidatd DocSets). - Because WKS uses those documents in the trained model, this effectively deleted the model, forcing me to restart training on initial data set. - End of night issue: 1.00 precision (perfect), 0.02 recall?
Day: | Sunday | Task(s) performed:
Date: | 2019-03-17 | Result:
Hours Worked: |  | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-03-18 | Result:
Hours Worked: |  | Problems encountered:
Day: | Tuesday | Task(s) performed: | - Uploading 114 documents into discovery for txt recovery later - withdraw 114 documents from pdf to txt - met with group to discuss integration - uplaod 114 txt documents into wks as sets for later annotation Later that day - Annotations of set 4, coreference annotations of set 1 and 2
Date: | 2019-03-19 | Result: | - Performance dropped dramatically, as version 2.0 was accidentally trained on only one dataset.
Hours Worked: | 6 | Problems encountered:
Day: | Wednesday | Task(s) performed: | - AnnotationSet06 completed
Date: | 2019-03-20 | Result: | - Trained as well. slightly better performance
Hours Worked: | 1 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2019-03-21 | Result:
Hours Worked: |  | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2019-03-22 | Result:
Hours Worked: |  | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-03-23 | Result:
Hours Worked: |  | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-03-24 | Result:
Hours Worked: |  | Problems encountered:
Day: | Monday | Task(s) performed: | - AnnotationSet07 AnnotationSet08 AnnotationSet09 - CoreferenceSet03 CoreferenceSet04 CoreferenceSet05 CoreferenceSet06 CoreferenceSet07 CoreferenceSet08 CoreferenceSet09
Date: | 2019-03-25 | Result: | - Seems like coreference does not affect mention accuracy like I thought it would. Sitting at about 0.87:0.57::precision:recall. Think highest mention accuracy is random, as training/testing sets vary
Hours Worked: | 6 | Problems encountered:

## Jay Patel
COMP4710 Status Report - Member Timesheet
Project Name: |  | TitleSearch
Member: |  | Jay Patel
Week Ending: |  | 2019-03-25
Cycle: |  | CYCLE 1
Team Member Work Summary
Monday | Tuesday | Task(s) performed:
Date: | 2019-02-26 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2019-02-27 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed: | Added initial UI for validating a WarrantyDeed before continuing to create house history chain of using warranty deeds.
Date: | 2019-02-28 | Result: | Initial UI was setup.
Hours Worked: | 6 | Problems encountered: | In order to show the PDF embedded into the JSP page to show allow the side by side comparison requires tracking the WarrantyDeed object inside of the house history array using an index value. This index has to be passed between a ShowPDF servlet and the main PerformTitleSearch servlet so that the ShowPDF servlet knows which WarrantyDeed object's pdf property to display as a response.
Day: | Friday | Task(s) performed:
Date: | 2019-03-01 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-03-02 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-03-03 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-03-04 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-03-05 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2019-03-06 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2019-03-07 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2019-03-08 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed: | Updated the validation UI to be able to show multiple warranty deeds for validation. The validation UI is hidden until a "Validate" button is clicked next to the warranty deed name and can be toggled to hide or show the validation of the warranty deed.
Date: | 2019-03-09 | Result: | The user can now select and validate any warranty deed in the entire house history chain at any step of the process when building the history.
Hours Worked: | 3 | Problems encountered: | None.
Day: | Sunday | Task(s) performed:
Date: | 2019-03-10 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-03-11 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-03-12 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed: | Met with sponsor to get feedback on the warranty deed validation UI. Discussed the WarrantyDeed object in detail to determine the properties it will require to describe the entire warranty deed.
Date: | 2019-03-13 | Result: | Received feedback on the UI and new requirements.
Hours Worked: | 1 | Problems encountered: | None.
Day: | Thursday | Task(s) performed:
Date: | 2019-03-14 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed: | Started the process on creating a new house history UI that displays the information contained inside of a WarrantyDeed object into a HTML Table. Each row of the table represents one WarrantyDeed object. The last cell links to the new updated validation UI for the WarrantyDeed object.
Date: | 2019-03-15 | Result: | Partial completion of the house history UI.
Hours Worked: | 3 | Problems encountered: | None.
Day: | Saturday | Task(s) performed: | Worked on connecting and updating the WarrantyDeed information objects from the user input in the validation UI. Since the WarrantyDeed objects only contain information. The UI is responsible for formatting the data to match the requirements for a house history report.
Date: | 2019-03-16 | Result: | Almost all of the data contained in the WarrantyDeed object can be formatted to be displayed properly in the house history report and the validation UI.
Hours Worked: | 8 | Problems encountered: | There is no validation currently for checking the changes submitted by the user using the validation UI. The code currently attempts to update the WarrantyDeed object with the passed in changes.
Day: | Sunday | Task(s) performed:
Date: | 2019-03-17 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-03-18 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Tuesday | Task(s) performed: | Group meeting to discuss the project integration using each of the individual Manager classes developed independently by the team.
Date: | 2019-03-19 | Result: | Gained a better understanding for integrating the project.
Hours Worked: | 1 | Problems encountered: | None.
Day: | Wednesday | Task(s) performed:
Date: | 2019-03-20 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2019-03-21 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed: | Met with sponsor to report the team's progress. Received feedback on the house history UI that was developed after the one-on-one meeting with sponsor on 3/13/2019.
Date: | 2019-03-22 | Result: | Successful
Hours Worked: | 1 | Problems encountered: | None.
Day: | Saturday | Task(s) performed:
Date: | 2019-03-23 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-03-24 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-03-25 | Result:
Hours Worked: | 0 | Problems encountered:

## Mina Narayanan
COMP4710 Status Report - Member Timesheet
Project Name: |  | TitleSearch
Member: |  | Mina Narayanan
Week Ending: |  | 2019-03-26
Cycle: |  | CYCLE 2
Team Member Work Summary
Monday | Tuesday | Task(s) performed: | N/A
Date: | 2019-02-26 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed: | Added functionality to BeautifulSoupAPI that allows the user to search old index books in different time periods
Date: | 2019-02-27 | Result: | More functionality available to user
Hours Worked: | 4 | Problems encountered: | Some names cannot be searched for in a given for each time period, i.e. deeds with names beginning with the letter T are not available from 1800 - 1945
Day: | Thursday | Task(s) performed: | N/A
Date: | 2019-02-28 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed: | N/A
Date: | 2019-03-01 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed: | N/A
Date: | 2019-03-02 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | N/A
Date: | 2019-03-03 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed: | N/A
Date: | 2019-03-04 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2019-03-05 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed: | N/A
Date: | 2019-03-06 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed: | N/A
Date: | 2019-03-07 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed: | N/A
Date: | 2019-03-08 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed: | N/A
Date: | 2019-03-09 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | N/A
Date: | 2019-03-10 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed: | N/A
Date: | 2019-03-11 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2019-03-12 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed: | N/A
Date: | 2019-03-13 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed: | Explored functions of Watson Knowledge Studio and Watson Natural Language Understanding
Date: | 2019-03-14 | Result: | More knowledge about IBM tools
Hours Worked: | 1 | Problems encountered:
Day: | Friday | Task(s) performed: | N/A
Date: | 2019-03-15 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed: | N/A
Date: | 2019-03-16 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | N/A
Date: | 2019-03-17 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed: | N/A
Date: | 2019-03-18 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Tuesday | Task(s) performed: | Group meeting to discuss project integration
Date: | 2019-03-19 | Result: | Better understanding of how Manager classes communicate
Hours Worked: | 1 | Problems encountered:
Day: | Wednesday | Task(s) performed: | N/A
Date: | 2019-03-20 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed: | N/A
Date: | 2019-03-21 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed: | Meeting with Trey to discuss progress made by individual group members
Date: | 2019-03-22 | Result: | Better grasp on people's tasks as well as problems they encountered
Hours Worked: | 1 | Problems encountered:
Day: | Saturday | Task(s) performed: | N/A
Date: | 2019-03-23 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | Merged work in the website-searchBookAndPage branch with work in a branch dedicated solely to the BeautifulSoupAPI
Date: | 2019-03-24 | Result: | More cohesive code
Hours Worked: | 1 | Problems encountered:
Day: | Monday | Task(s) performed: | Integrated TitleSearchManager and BeautifulSoupAPI, created a WarrantyDeed object with data returned from the BeautifulSoup API
Date: | 2019-03-25 | Result: | More modular system design, easier to access Warranty Deed data
Hours Worked: | 5 | Problems encountered:

## AJ Hancher
COMP4710 Status Report - Member Timesheet
Project Name: |  | TitleSearch
Member: |  | AJ Hancher
Week Ending: |  | 2019-03-26
Cycle: |  | CYCLE 2
Team Member Work Summary
Monday | Tuesday | Task(s) performed:
Date: | 2019-02-26 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2019-02-27 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2019-02-28 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2019-03-01 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-03-02 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-03-03 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-03-04 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-03-05 | Result:
Hours Worked: |  | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2019-03-06 | Result:
Hours Worked: |  | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2019-03-07 | Result:
Hours Worked: |  | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2019-03-08 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-03-09 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-03-10 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-03-11 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-03-12 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2019-03-13 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2019-03-14 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2019-03-15 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-03-16 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | Met with Jay to discuss how I saw the database manager API's being implemented
Date: | 2019-03-17 | Result: | Started work on the apis
Hours Worked: | 3 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-03-18 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-03-19 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2019-03-20 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed: | Continued the work on the database manager APi
Date: | 2019-03-21 | Result: | Got a model that can be used to test
Hours Worked: | 2 | Problems encountered:
Day: | Friday | Task(s) performed: | Met with our sponor
Date: | 2019-03-22 | Result: | Laid out a plan for the rest of the semester
Hours Worked: | 1 | Problems encountered:
Day: | Saturday | Task(s) performed: | Worked on integrating the database with the other parts of the project
Date: | 2019-03-23 | Result: | Still in progress
Hours Worked: | 6 | Problems encountered: | Connecting the database to a cloud service instance
Day: | Sunday | Task(s) performed: | Set up a meeting with our sponsor for help with connecitng the database to ibm cloud
Date: | 2019-03-24 | Result: | Meeting set up for 3/23/19]
Hours Worked: | 1 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-03-25 | Result:
Hours Worked: | 0 | Problems encountered: